## Project Timeline
layer_name | event_id | event_name | notes | start_date | end_date | icon | color
Develop |  | Culture Assessments | Chat with HR beforehand. | Jun 01, 2020 | Jun 30, 2020 | solid circle | #BCAAA4
Develop |  | Define Governance |  | ~Feb 05, 2020 | ~Feb 25, 2020 | solid circle | #BCAAA4
Develop |  | Document Existing States |  | Feb 01, 2020 | Feb 15, 2020 | solid circle | #616161
Develop |  | Document Future States |  | Feb 10, 2020 | Feb 25, 2020 | solid circle | #212121
Develop |  | Process Alignment |  | Jul 01, 2020 |  | solid bullseye | #212121
Develop |  | Skill Assessments |  | May 03, 2020 | May 22,2020 | solid circle | #607D8B
Develop |  | Stakeholder Analysis |  | ~Apr 5, 2020 | ~Apr 25, 2020 | solid circle | #78909C
Design |  | Impact Assessment |  | Feb 10, 2020 | Feb 29, 2020 | solid circle | #455A64
Design |  | Mentor Leaders |  | Feb 15, 2020 | Apr 30, 2020 | solid circle | #9E9E9E
Design |  | Performance Mgmt |  | ~May 15, 2020 | ~Jul 30, 2020 | solid circle | #616161
Design |  | Stakeholder Comm Plan |  | Mar 20, 2020 | Apr 15, 2020 | solid circle | #283593